## Slide 1: Chapter 4: Project Integration Management
Information Technology Project
Management, Eighth Edition
Note: See the text itself for full citations.

## Slide 2: Learning Objectives, Part 1
Describe an overall framework for project integration management as it relates to the other project management knowledge areas and the project life cycle
Discuss the strategic planning process and apply different project selection methods
Explain the importance of creating a project charter to formally initiate projects
Describe project management plan development, understand the content of these plans, and review approaches for creating them

## Slide 3: Learning Objectives, Part 2
Explain project execution, its relationship to project planning, the factors related to successful results, and tools and techniques to assist in directing and managing project work
Describe the process of monitoring and controlling a project
Understand the integrated change control process, planning for and managing changes on information technology (IT) projects, and developing and using a change control system
Explain the importance of developing and following good procedures for closing projects
Describe how software can assist in project integration management

## Slide 4: The Key to Overall Project Success: Good Project Integration Management
Project managers must coordinate all of the other knowledge areas throughout a project’s life cycle
Many new project managers have trouble looking at the “big picture” and want to focus on too many details (See opening case for a real example)
Project integration management is not the same thing as software integration

## Slide 5: Project Integration Management Processes, Part 1
1. Developing the project charter involves working with stakeholders to create the document that formally authorizes a project—the charter.
2. Developing the project management plan involves coordinating all planning efforts to create a consistent, coherent document—the project management plan.
3. Directing and managing project work involves carrying out the project management plan by performing the activities included in it.

## Slide 6: Project Integration Management Processes, Part 2
Monitoring and controlling project work involves overseeing activities to meet the performance objectives of the project
Performing integrated change control involves identifying, evaluating, and managing changes throughout the project life cycle.
Closing the project or phase involves finalizing all activities to formally close the project or phase.

## Slide 7: Figure 4-1. Project Integration Management Summary

## Slide 8: What Went Wrong?
The Surrey police force began looking into replacing its criminal intelligence system in 2005, but the project was finally cancelled in 2013, and the old system was replaced with a much less expensive one used by thirteen other forces
The person in charge of the project would not take responsibility for it
An audit report said the project was beyond their in-house capabilities and experience
Organizations must make the right staffing/outsourcing decisions

## Slide 9: Strategic Planning and Project Selection
Strategic planning involves determining long-term objectives, predicting future trends, and projecting the need for new products and services
Organizations often perform a SWOT analysis
  analyzing Strengths, Weaknesses, Opportunities, and Threats
As part of strategic planning, organizations
  identify potential projects
  use realistic methods to select which projects to work on
  formalize project initiation by issuing a project charter

## Slide 10: Figure 4-2. Mind Map of a SWOT Analysis to Help Identify Potential Projects

## Slide 11: Figure 4-3. Information Technology Planning Process

## Slide 12: Best Practice
A 2013 survey identified companies most admired for their ability to apply IT-related business capabilities for competitive advantage
Best practices of these companies include:
  Customer-driven IT is essential
  IT can enable branding and customer recruitment
  Keep improving

## Slide 13: Methods for Selecting Projects
There are usually more projects than available time and resources to implement them
Methods for selecting projects include:
  focusing on broad organizational needs
  categorizing information technology projects
  performing net present value or other financial analyses
  using a weighted scoring model
  implementing a balanced scorecard

## Slide 14: Focusing on Broad Organizational Needs
It is often difficult to provide strong justification for many IT projects, but everyone agrees they have a high value
“It is better to measure gold roughly than to count pennies precisely”
Three important criteria for projects:
  There is a need for the project
  There are funds available
  There’s a strong will to make the project succeed

## Slide 15: Categorizing IT Projects
One categorization is whether the project addresses
  a problem
  an opportunity, or
  a directive
Another categorization is how long it will take to do and when it is needed
Another is the overall priority of the project

## Slide 16: Financial Analysis of Projects
Financial considerations are often an important consideration in selecting projects
Three primary methods for determining the projected financial value of projects:
  Net present value (NPV) analysis
  Return on investment (ROI)
  Payback analysis

## Slide 17: Net Present Value Analysis
Net present value (NPV) analysis is a method of calculating the expected net monetary gain or loss from a project by discounting all expected future cash inflows and outflows to the present point in time
Projects with a positive NPV should be considered if financial value is a key criterion
The higher the NPV, the better

## Slide 18: Figure 4-4. Net Present Value Example
Empty cell | A | B | C | D | E | F | G
1 | Discount rate | 10% | Empty cell | Empty cell | Empty cell | Empty cell | Empty cell
2 | Empty cell | Empty cell | Empty cell | Empty cell | Empty cell | Empty cell | Empty cell
3 | Project 1 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
4 | Benefits | $0 | $2,000 | $3,000 | $4,000 | $5,000 | 14,000
5 | Costs | $5,000 | $1,000 | $1,000 | $1,000 | $1,000 | $9,000
6 | Cash flow | ($5,000) | $1,000 | $2,000 | $3,000 | $4,000 | $5,000 (with arrow. Note that totals are equal, but Net Present Values are not because of the time value of money)
7 | Net Present Value (arrow) | $2,316 | Empty cell | Empty cell | Empty cell | Empty cell | Empty cell
8 | Empty cell | Formula=npv(b1,b6:f6) | Empty cell | Empty cell | Empty cell | Empty cell | Empty cell
9 | Empty cell | Empty cell | Empty cell | Empty cell | Empty cell | Empty cell | Empty cell
10 | Project 2 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
11 | Benefits | $1,000 | $2,000 | $4,000 | $4,000 | $4,000 | $15,000
12 | Costs | $2,000 | $2,000 | $2,000 | $2.000 | $2,000 | $10,000
13 | Cash flow | ($1,000) | $0 | $2,000 | $2,000 | $2,000 | $5,000 (with arrow. Note that totals are equal, but Net Present Values are not because of the time value of money)
14 | Net present value (arrow) | $3,201 | Empty cell | Empty cell | Empty cell | Empty cell | Empty cell
15 | Empty cell | Formula=npv(b1,b13:f13) | Empty cell | Empty cell | Empty cell | Empty cell | Empty cell
16 | Empty cell | Empty cell | Empty cell | Empty cell | Empty cell | Empty cell | Empty cell
17 | Empty cell | Empty cell | Empty cell | Empty cell | Empty cell | Empty cell | Empty cell

## Slide 19: Figure 4-5. JWD Consulting NPV Example
Discount Rate | 8 percent | Empty cell | Empty cell | Empty cell | Empty cell | Empty cell
Assume the project is completed in Year 0 | Empty cell | Empty cell | Year | Empty cell | Empty cell | Empty cell
Empty cell | 0 | 1 | 2 | 3 | Total | Empty cell
Costs | 140,000 | 40,000 | 40,000 | 40,000 | Empty cell | Empty cell
Discount factor | 1 | .93 | .86 | .79 | Empty cell | Empty cell
Discounted benefits | 0 | 186,000 | 172,000 | 158,000 | 516,000 | Empty cell
Discounted benefits - costs | (140,000) | 148,800 | 137,600 | 126,400 | (Net present value) 272,800 (arrow pointing) | NPV (has arrow)
Cumulative benefits – costs | (140,000) | 8,800 (Payback In Year 1) | 146,400 | 272,800 | Empty cell | Empty cell
ROI (with arrow) | 112% (return on investment) | Payback in Year 1 (with arrow pointing up) | Empty cell | Empty cell | Empty cell | Empty cell
Note: See the template called business_case_financials.xls

## Slide 20: NPV Calculations
Determine estimated costs and benefits for the life of the project and the products it produces
Determine the discount rate (check with your organization on what to use)
Calculate the NPV (see text for details)
Notes: Some organizations consider the investment year as year 0, while others start in year 1. Some people entered costs as negative numbers, while others do not. Check with your organization for their preferences

## Slide 21: Return on Investment
Return on investment (ROI) is calculated by subtracting the project costs from the benefits and then dividing by the costs
  ROI = (total discounted benefits - total discounted costs) / discounted costs
The higher the ROI, the better
Many organizations have a required rate of return or minimum acceptable rate of return on investment for projects
Internal rate of return (IRR) can by calculated by finding the discount rate that makes the NPV equal to zero

## Slide 22: Payback Analysis
Another important financial consideration is payback analysis
The payback period is the amount of time it will take to recoup, in the form of net cash inflows, the total dollars invested in a project
Payback occurs when the net cumulative discounted benefits equals the costs
Many organizations want IT projects to have a fairly short payback period

## Slide 23: Figure 4-6. Charting the Payback Period

## Slide 24: Weighted Scoring Model
A weighted scoring model is a tool that provides a systematic process for selecting projects based on many criteria
    Identify criteria important to the project selection process
    Assign weights (percentages) to each criterion so they add up to 100%
    Assign scores to each criterion for each project
    Multiply the scores by the weights and get the total weighted scores
The higher the weighted score, the better

## Slide 25: Figure 4-7. Sample Weighted Scoring Model for Project Selection
Empty cell | A | B | C | D | E | F
1 | Criteria | Weight | Project 1 | Project 2 | Project 3 | Project 4
2 | Supports key business objectives | 25% | 90 | 90 | 50 | 20
3 | Has strong internal sponsor | 15% | 70 | 90 | 50 | 20
4 | Has strong customer support | 15% | 50 | 90 | 50 | 20
5 | Uses realistic level of technology | 10% | 25 | 90 | 50 | 70
6 | Can be implemented in one year or less | 5% | 20 | 20 | 50 | 90
7 | Provides positive NPV | 20% | 50 | 70 | 50 | 50
8 | Has low risk in meeting scope, time, and cost goals | 10% | 20 | 50 | 50 | 90
9 | Weighted Project Scores | 100% | 56 | 78.5 | 50 | 41.5

## Slide 26: Implementing a Balanced Scorecard
Drs. Robert Kaplan and David Norton developed this approach to help select and manage projects that align with business strategy
A balanced scorecard
  is a methodology that converts an organization’s value drivers, such as customer service, innovation, operational efficiency, and financial performance, to a series of defined metrics
See www.balancedscorecard.org for more information

## Slide 27: Developing a Project Charter
After deciding what project to work on, it is important to let the rest of the organization know
A project charter is a document that formally recognizes the existence of a project and provides direction on the project’s objectives and management
Key project stakeholders should sign a project charter to acknowledge agreement on the need and intent of the project; a signed charter is a key output of project integration management

## Slide 28: Inputs for Developing a Project Charter
A project statement of work
A business case
Agreements
Enterprise environmental factors
Organizational process assets, which include formal and informal plans, policies, procedures, guidelines, information systems, financial systems, management systems, lessons learned, and historical information

## Slide 29: Table 4-1. Project Charter for the DNA-Sequencing Instrument Completion Project
Project Title: DNA-Sequencing Instrument Completion Project Date of Authorization: February 1 Project Start Date: February 1 Projected Finish Date: November 1
Key Schedule Milestones: Complete first version of the software by June 1 Complete production version of the software by November 1
Budget Information: The firm has allocated $1.5 million for this project, and more funds are available if needed. The majority of costs for this project will be internal labor. All hardware will be outsourced.
Project Manager: Nick Carson, (650) 949-0707, ncarson@dnaconsulting.com
Project Objectives: The DNA-sequencing instrument project has been underway for three years. It is a crucial project for our company. This is the first charter for the project, and the objective is to complete the first version of the software for the instrument in four months and a production version in nine months.
Main Project Success Criteria: The software must meet all written specifications, be thoroughly tested, and be completed on time. The CEO will formally approve the project with advice from other key stakeholders.

## Slide 30: Table 4-1. Project Charter
Name | Role | Position | Contact Information
Ahmed Abrams | Sponsor | CEO | aabrams@dnaconsulting.com
Nick Carson | Project Manager | Manager | ncarson@dnaconsulting.com
Susan Johnson | Team Member | DNA expert | sjohnson@dnaconsulting.com
Renyong Chi | Team Member | Testing expert | rchi@dnaconsulting.com
Erik Haus | Team Member | Programmer | ehaus@dnaconsulting.com
Bill Strom | Team Member | Programmer | bstrom@dnaconsulting.com
Maggie Elliot | Team Member | Programmer | melliot@dnaconsulting.com

## Slide 31: Developing a Project Management Plan
A project management plan is a document used to coordinate all project planning documents and help guide a project’s execution and control
Plans created in the other knowledge areas are subsidiary parts of the overall project management plan

## Slide 32: Common Elements of a Project Management Plan
Introduction or overview of the project
Description of how the project is organized
Management and technical processes used on the project
Work to be done, schedule, and budget information

## Slide 33: Table 4-2. Sample Contents for a Software Project Management Plan (SPMP)
MAJOR SECTION HEADINGS | SECTION TOPICS
Overview | Purpose, scope, and objectives; assumptions and constraints; project deliverables; schedule and budget summary; evolution of the plan
Project Organization | External interfaces; internal structure; roles and Responsibilities
Managerial Process Plan | Start-up plans (estimation, staffing, resource acquisition; and project staff training plans); work plan (work activities, schedule, resource, and budget allocation); control plan; risk management plan; closeout plan
Technical Process Plans | Process model; methods, tools, and techniques; infrastructure Plan; product acceptance plan
Supporting Process Plans | Configuration management plan; verification and validation plan; documentation plan; quality assurance plan; reviews And audits; problem resolution plan; subcontractor manage- ment plan; process improvement plan
IEEE Standard 1058-1998. | Empty cell

## Slide 34: What the Winners Do
"The winners clearly spell out what needs to be done in a project, by whom, when, and how. For this they use an integrated toolbox, including PM tools, methods, and techniques…If a scheduling template is developed and used over and over, it becomes a repeatable action that leads to higher productivity and lower uncertainty. Sure, using scheduling templates is neither a breakthrough nor a feat. But laggards exhibited almost no use of the templates. Rather, in constructing schedules their project managers started with a clean sheet, a clear waste of time.“*
*Milosevic, Dragan and And Ozbay. “Delivering Projects: What the Winners Do.” Proceedings of the Project Management Institute Annual Seminars & Symposium (November 2001).

## Slide 35: Directing and Managing Project Work
Involves managing and performing the work described in the project management plan
The majority of time and money is usually spent on execution
The application area of the project directly affects project execution because the products of the project are produced during execution

## Slide 36: Coordinating Planning and Execution
Project planning and execution are intertwined and inseparable activities
Those who will do the work should help to plan the work
Project managers must solicit input from the team to develop realistic plans

## Slide 37: Providing Leadership and a Supportive Culture
Project managers must lead by example to demonstrate the importance of creating and then following good project plans
Organizational culture can help project execution by
  providing guidelines and templates
  tracking performance based on plans
Project managers may still need to break the rules to meet project goals, and senior managers must support those actions

## Slide 38: What Went Right?
2015 PMI report found that only 12 percent of organizations were considered to be high performers
Percentage remained unchanged in past few years
Organizations must make major cultural changes to improve

## Slide 39: Capitalizing on Product, Business, and Application Area Knowledge
It is often helpful for IT project managers to have prior technical experience
On small projects, the project manager may be required to perform some of the technical work or mentor team members to complete the projects
On large projects, the project manager must understand the business and application area of the project

## Slide 40: Project Execution Tools and Techniques
Expert judgment: Experts can help project managers and their teams make many decisions related to project execution
Meetings: Meetings allow people to develop relationships, pick up on important body language or tone of voice, and have a dialogue to help resolve problems.
Project management information systems: There are hundreds of project management software products available on the market today, and many organizations are moving toward powerful enterprise project management systems that are accessible via the Internet
See the What Went Right? example of Kuala Lumpur’s Integrated Transport Information System on p. 169

## Slide 41: Monitoring and Controlling Project Work
Changes are inevitable on most projects, so it’s important to develop and follow a process to monitor and control changes
Monitoring project work includes collecting, measuring, and disseminating performance information
A baseline is the approved project management plan plus approved changes

## Slide 42: Media Snapshot
The 2002 Olympic Winter Games and Paralympics took five years to plan and cost more than $1.9 billion. PMI awarded the Salt Lake Organizing Committee (SLOC) the Project of the Year award for delivering world-class games.
Four years before the Games began, the SLOC used a Primavera software-based system with a cascading color-coded WBS to integrate planning…The SLOC also used an Executive Roadmap, a one-page list of the top 100 Games-wide activities, to keep executives apprised of progress. Activities were tied to detailed project information within each department’s schedule. A 90-day highlighter showed which managers were accountable for each integrated activity.
Fraser Bullock, SLOC Chief Operating Officer and Chief, said, “We knew when we were on and off schedule and where we had to apply additional resources. The interrelation of the functions meant they could not run in isolation—it was a smoothly running machine.”*
*Foti, Ross, “The Best Winter Olympics, Period,” PM Network (January 2004) 23.

## Slide 43: Performing Integrated Change Control
Three main objectives are:
  Influencing the factors that create changes to ensure that changes are beneficial
  Determining that a change has occurred
  Managing actual changes as they occur

## Slide 44: Change Control on Information Technology Projects
Former view: The project team should strive to do exactly what was planned on time and within budget
Problem: Stakeholders rarely agreed up-front on the project scope, and time and cost estimates were inaccurate
Modern view: Project management is a process of constant communication and negotiation
Solution: Changes are often beneficial, and the project team should plan for them

## Slide 45: Change Control System
A change control system is a formal, documented process that describes when and how official project documents and work may be changed
Describes who is authorized to make changes and how to make them

## Slide 46: Change Control Board (CCB)
A change control board is a formal group of people responsible for approving or rejecting changes on a project
CCBs provide guidelines for preparing change requests, evaluate change requests, and manage the implementation of approved changes
Includes stakeholders from the entire organization

## Slide 47: Making Timely Changes
Some CCBs only meet occasionally, so it may take too long for changes to occur
Some organizations have policies in place for time-sensitive changes
  “48-hour policy” allows project team members to make decisions, then they have 48 hours to reverse the decision pending senior management approval
  Delegate changes to the lowest level possible, but keep everyone informed of changes

## Slide 48: Global Issues
Rapid changes in technology, such as the increased use of mobile roaming for communications, often cause governments around the world to take action.
Incompatible hardware, software, and networks can make communications difficult in some regions, and a lack of competition can cause prices to soar.
Fortunately, a group called the Organisation for Economic Co-operation and Development (OECD) promotes policies that will improve the economic and social well-being of people around the world.
In February 2012, the OECD called upon its members’ governments to boost competition in international mobile roaming markets.
By the end of 2013, wireless broadband penetration grew to 72.4% in the OECD area

## Slide 49: Configuration Management
Configuration management ensures that the descriptions of the project’s products are correct and complete
Involves identifying and controlling the functional and physical design characteristics of products and their support documentation
Configuration management specialists identify and document configuration requirements, control changes, record and report changes, and audit the products to verify conformance to requirements
See www.icmhq.com for more information

## Slide 50: Table 4-3. Suggestions for Performing Integrated Change Control
View project management as a process of constant communication and negotiation.
Plan for change.
Establish a formal change control system, including a change control board (CCB).
Use effective configuration management.
Define procedures for making timely decisions on smaller changes.
Use written and oral performance reports to help identify and manage change.
Use project management and other software to help manage and communicate changes.
Focus on leading the project team and meeting overall project goals and expectations.

## Slide 51: Closing Projects or Phases
To close a project or phase, you must finalize all activities and transfer the completed or cancelled work to the appropriate people
Main outputs include
  Final product, service, or result transition
  Organizational process asset updates

## Slide 52: Using Software to Assist in Project Integration Management
Several types of software can be used to assist in project integration management
  Documents can be created with word processing software
  Presentations are created with presentation software
  Tracking can be done with spreadsheets or databases
  Communication software can facilitate communications
  Project management software can pull everything together and show detailed and summarized information

## Slide 53: Figure 4-8. Sample Portfolio Management Software Screen
Source: www.projectmanager.com

## Slide 54: Chapter Summary
Project integration management involves coordinating all of the other knowledge areas throughout a project’s life cycle
Main processes include
  Develop the project charter
  Develop the project management plan
  Direct and manage project execution
  Monitor and control project work
  Perform integrated change control
  Close the project or phase