## Slide 1: Chapter 9: Project Human Resource Management
Information Technology Project Management, Eighth Edition
Note: See the text itself for full citations.

## Slide 2: Learning Objectives, Part 1
Explain the importance of good human resource management on projects, including the current state of the global IT workforce and future implications for it
Define project human resource management and understand its processes
Summarize key concepts for managing people by understanding theories of motivation, influence, and power; how people and teams can become more effective; emotional intelligence; and leadership

## Slide 3: Learning Objectives, Part 2
Discuss human resource management planning and be able to create a human resource plan, project organizational chart, responsibility assignment matrix, and resource histogram
Understand important issues involved in project staff acquisition and explain the concepts of resource assignments, resource loading, and resource leveling
Assist in team development with training, team-building activities, and reward systems
Explain and apply several tools and techniques to help manage a project team and summarize general advice on managing teams
Describe how project management software can assist in project human resource management

## Slide 4: The Importance of Human Resource Management
Many corporate executives have said, “People are our most important asset”
People determine the success and failure of organizations and projects

## Slide 5: The Global IT Workforce
Although there have been ups and downs in the IT labor market, there will always be a need for good IT workers
By the end of 2014, there were almost 3 billion Internet users and 2.3 billion mobile-broadband subscriptions
By 2020, ICT spending is projected to grow to nearly $5 trillion
Project management was number two on Computerworld’s hottest skill list for 2015
PMI estimates demand for 15.7 million project management jobs from 2010 to 2020

## Slide 6: Implications for the Future of IT Human Resource Management
Proactive organizations are addressing workforce needs by
  improving benefits
  redefining work hours and incentives
  finding future workers

## Slide 7: Global Issues
In 2013 Yahoo’s CEO issued a memo stating that employees could no longer work from home, causing quite a stir throughout the world
Diebold’s CEO took the opposite approach and started recruiting employees who wanted to work from home, luring the best and brightest workers from Yahoo and other companies cutting back on telecommuting
The Huffington Post believes that telecommuting has won, and even Yahoo has softened its stance

## Slide 8: What Went Wrong?
A 2014 report by CompTIA found a gap between skills that employers wanted and what they actually found in the IT workforce
68 percent of IT firms report having a very challenging time finding new staff
58 percent of businesses are concerned about the quality and quantity of IT talent available for hire
The number one strategy to handle understaffing is requiring workers to put in more hours

## Slide 9: What is Project Human Resource Management?
Making the most effective use of the people involved with a project
Processes include
  Planning human resource management: identifying and documenting project roles, responsibilities, and reporting relationships
  Acquiring the project team: getting the needed personnel assigned to and working on the project
  Developing the project team: building individual and group skills to enhance project performance
  Managing the project team: tracking team member performance, motivating team members, providing timely feedback, resolving issues and conflicts, and coordinating changes to help enhance project performance

## Slide 10: Figure 9-1. Project Human Resource Management Summary

## Slide 11: Keys to Managing People
Psychologists and management theorists have devoted much research and thought to the field of managing people at work
Important areas related to project management include
  motivation theories
  influence and power
  Effectiveness
  Emotional intelligence
  Leadership

## Slide 12: Intrinsic and Extrinsic Motivation
Intrinsic motivation causes people to participate in an activity for their own enjoyment
Extrinsic motivation causes people to do something for a reward or to avoid a penalty
For example, some children take piano lessons for intrinsic motivation (they enjoy it) while others take them for extrinsic motivation (to get a reward or avoid punishment)

## Slide 13: Maslow’s Hierarchy of Needs
Abraham Maslow argued that humans possess unique qualities that enable them to make independent choices, thus giving them control of their destiny
Maslow developed a hierarchy of needs which states that people’s behaviors are guided or motivated by a sequence of needs

## Slide 14: Figure 9-2. Maslow’s Hierarchy of Needs

## Slide 15: Herzberg’s Motivational and Hygiene Factors
Frederick Herzberg wrote several famous books and articles about worker motivation. He distinguished between
  motivational factors: achievement, recognition, the work itself, responsibility, advancement, and growth, which produce job satisfaction
  hygiene factors: cause dissatisfaction if not present, but do not motivate workers to do more. Examples include larger salaries, more supervision, and a more attractive work environment

## Slide 16: Table 9-1: Examples of Herzberg’s Hygiene Factors and Motivators
HYGIENE FACTORS | MOTIVATORS
Larger salaries | Achievement
More supervision | Recognition
More attractive work environment | Work itself
Computer or other required equipment | Responsibility
Health benefits | Advancement
Training | Growth

## Slide 17: Media Snapshot
RSA Animate used its popular whiteboard drawing technique to summarize key points from Pink’s book in a YouTube video called “Drive: The surprising truth about what motivates us”
Pink suggests that managers focus on the following three motivators:
  Autonomy
  Mastery
  Purpose

## Slide 18: McClelland’s Acquired-Needs Theory
Specific needs are acquired or learned over time and shaped by life experiences, including:
  Achievement (nAch): Achievers like challenging projects with achievable goals and lots of feedback
  Affiliation (nAff): People with high nAff desire harmonious relationships and need to feel accepted by others, so managers should try to create a cooperative work environment for them
  Power: (nPow): People with a need for power desire either personal power (not good) or institutional power (good for the organization). Provide institutional power seekers with management opportunities

## Slide 19: McGregor’s Theory X and Y
Douglas McGregor popularized the human relations approach to management in the 1960s
Theory X: assumes workers dislike and avoid work, so managers must use coercion, threats and various control schemes to get workers to meet objectives
Theory Y: assumes individuals consider work as natural as play or rest and enjoy the satisfaction of esteem and self-actualization needs
Theory Z: introduced in 1981 by William Ouchi and is based on the Japanese approach to motivating workers, emphasizing trust, quality, collective decision making, and cultural values

## Slide 20: Thamhain and Wilemon’s Ways to Have Influence on Projects, Part 1
Authority: the legitimate hierarchical right to issue orders
Assignment: the project manager's perceived ability to influence a worker's later work assignments
Budget: the project manager's perceived ability to authorize others' use of discretionary funds
Promotion: the ability to improve a worker's position
Money: the ability to increase a worker's pay and benefits

## Slide 21: Thamhain and Wilemon’s Ways to Have Influence on Projects, Part 2
Penalty: the project manager's ability to cause punishment
Work challenge: the ability to assign work that capitalizes on a worker's enjoyment of doing a particular task
Expertise: the project manager's perceived special knowledge that others deem important
Friendship: the ability to establish friendly personal relationships between the project manager and others

## Slide 22: Ways to Influence that Help and Hurt Projects
Projects are more likely to succeed when project managers influence with
  expertise
  work challenge
Projects are more likely to fail when project managers rely too heavily on
  authority
  money
  penalty

## Slide 23: Power
Power is the potential ability to influence behavior to get people to do things they would not otherwise do
Types of power include
  Coercive
  Legitimate
  Expert
  Reward
  Referent

## Slide 24: Covey and Improving Effectiveness
Project managers can apply Covey’s 7 habits to improve effectiveness on projects
  Be proactive
  Begin with the end in mind
  Put first things first
  Think win/win
  Seek first to understand, then to be understood
  Synergize
  Sharpen the saw

## Slide 25: Empathic Listening and Rapport
Good project managers are empathic listeners - they listen with the intent to understand
Before you can communicate with others, you have to have rapport – a relation of harmony, conformity, accord, or affinity
Mirroring is the matching of certain behaviors of the other person, a technique to help establish rapport
IT professionals need to develop empathic listening and other people skills to improve relationships with users and other stakeholders

## Slide 26: Emotional Intelligence
Howard Gardner’s book Frames of Mind: The Theory of Multiple Intelligences introduced the concept of using more than one way to think of and measure human intelligence
Emotional intelligence (EI) is knowing and managing one’s own emotions and understanding the emotions of others for improved performance
71 percent of U.S. hiring managers say they value EI more than IQ

## Slide 27: Leadership
There is no one best way to be a leader
Most experts agree that the best leaders are able to adapt their style to needs of the situation
Daniel Goleman, author of Emotional Intelligence and Primal Leadership, describes six leadership styles:
  Visionary
  Coaching
  Affiliative
  Democratic
  Pacesetting
  Commanding

## Slide 28: What Went Right?
PMI introduced the PMI Talent Triangle in 2015 to emphasize the need for more than technical skills for project managers
The Talent Triangle includes:
  Technical project management
  Strategic and business management
  Leadership

## Slide 29: Developing the Human Resource Plan
Involves identifying and documenting project roles, responsibilities, and reporting relationships
Contents include
  project organizational charts
  staffing management plan
  responsibility assignment matrixes
  resource histograms

## Slide 30: Figure 9-3. Sample Organizational Chart for a Large IT Project

## Slide 31: Figure 9-4. Work Definition and Assignment Process

## Slide 32: Responsibility Assignment Matrices
A responsibility assignment matrix (RAM) is a matrix that maps the work of the project as described in the WBS to the people responsible for performing the work as described in the OBS
Can be created in different ways to meet unique project needs

## Slide 33: Figure 9-5. Sample Responsibility Assignment Matrix (RAM)
empty cell | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.1.6 | 1.1.7 | 1.1.8
Systems Engineering | R | R P | empty cell | empty cell | empty cell | empty cell | R | empty cell
Software Development | empty cell | empty cell | R P | empty cell | empty cell | empty cell | empty cell | empty cell
Hardware Development | empty cell | empty cell | empty cell | R P | empty cell | empty cell | empty cell | empty cell
Test Engineering | P | empty cell | empty cell | empty cell | empty cell | empty cell | empty cell | empty cell
Quality Assurance | empty cell | empty cell | empty cell | empty cell | R P | empty cell | empty cell | empty cell
Configuration Management | empty cell | empty cell | empty cell | empty cell | empty cell | R P | empty cell | empty cell
Integrated Logistics Support | empty cell | empty cell | empty cell | empty cell | empty cell | empty cell | P | empty cell
Training | empty cell | empty cell | empty cell | empty cell | empty cell | empty cell | empty cell | R P

## Slide 34: Table 9-2. Sample RACI Chart
        R = responsibility
        A = accountability, only one A per task
        C = consultation
        I = informed
Note that some people reverse the definitions of responsible and accountable.
Empty cell | Group A | Group B | Group C | Group D | Group E
Test Plans | R | A | C | C | I
Unit Test | C | I | R | A | I
Integration Test | A | R | I | C | C
System Test | I | C | A | I | R
User Acceptance Test | R | I | C | R | A

## Slide 35: Staffing Management Plans and Resource Histograms
A staffing management plan describes when and how people will be added to and taken off the project team
A resource histogram is a column chart that shows the number of resources assigned to a project over time

## Slide 36: Figure 9-6. Sample Resource Histogram

## Slide 37: Acquiring the Project Team
Acquiring qualified people for teams is crucial
The project manager who is the smartest person on the team has done a poor job of recruiting!
It’s important to assign the appropriate type and number of people to work on projects at the appropriate times

## Slide 38: Resource Assignment
Staffing plans and good hiring procedures are important, as are incentives for recruiting and retention
  Some companies give their employees one dollar for every hour a new person they helped hire works
  Some organizations allow people to work from home as an incentive
Enrollment in U.S. computer science and engineering programs has dropped almost in half since 2000, and one-third of U.S. workers were over the age of 50 by 2010
CIO’s researchers suggest that organizations rethink hiring practices and incentives to hire and retain IT talent

## Slide 39: Best Practice
Best practices can be applied to include the best places for people to work
  For example, Fortune Magazine lists the “100 Best Companies to Work For” in the United States every year, with Google taking the honors for the sixth time in 2015
  Working Mothers Magazine lists the best companies in the U.S. for women based on benefits for working families
  The Timesonline (www.timesonline.co.uk) provides the Sunday Times list of the 100 Best Companies to Work For, a key benchmark against which UK companies can judge their Best Practice performance as employers

## Slide 40: Resource Loading
Resource loading refers to the amount of individual resources an existing schedule requires during specific time periods
Helps project managers develop a general understanding of the demands a project will make on the organization’s resources and individual people’s schedules
Overallocation means more resources than are available are assigned to perform work at a given time

## Slide 41: Figure 9-7. Sample Histogram Showing an Overallocated Individual

## Slide 42: Resource Leveling
Resource leveling is a technique for resolving resource conflicts by delaying tasks
The main purpose of resource leveling is to create a smoother distribution of resource usage and reduce overallocation

## Slide 43: Figure 9-8. Resource Leveling Example

## Slide 44: Benefits of Resource Leveling
When resources are used on a more constant basis, they require less management
It may enable project managers to use a just-in-time inventory type of policy for using subcontractors or other expensive resources
It results in fewer problems for project personnel and accounting department
It often improves morale

## Slide 45: Developing the Project Team
The main goal of team development is to help people work together more effectively to improve project performance
It takes teamwork to successfully complete most projects

## Slide 46: Tuckman Model of Team Development
Forming
Storming
Norming
Performing
Adjourning

## Slide 47: Training
Training can help people understand themselves, each other, and how to work better in teams
Team building activities include
  physical challenges
  psychological preference indicator tools

## Slide 48: Meyers-Briggs Type Indicator (MBTI)
MBTI is a popular tool for determining personality preferences and helping teammates understand each other
Four dimensions include:
  Extrovert/Introvert (E/I)
  Sensation/Intuition (S/N)
  Thinking/Feeling (T/F)
  Judgment/Perception (J/P)
NTs or rationals are attracted to technology fields
IT people vary most from the general population in not being extroverted or sensing

## Slide 49: Social Styles Profile
People are perceived as behaving primarily in one of four zones, based on their assertiveness and responsiveness:
  Drivers
  Expressives
  Analyticals
  Amiables
People on opposite corners (drivers and amiables, analyticals and expressives) may have difficulties getting along

## Slide 50: Figure 9-9. Social Styles

## Slide 51: DISC Profiles
Also uses a four-dimensional model of normal behavior
  Dominance
  Influence
  Steadiness
  Compliance
People in opposite quadrants can have problems understanding each other

## Slide 52: Figure 9-10. The DISC Profile

## Slide 53: Reward and Recognition Systems
Team-based reward and recognition systems can promote teamwork
Focus on rewarding teams for achieving specific goals
Allow time for team members to mentor and help each other to meet project goals and develop human resources

## Slide 54: Managing the Project Team
Project managers must lead their teams in performing various project activities
After assessing team performance and related information, the project manager must decide
  if changes should be requested to the project
  if corrective or preventive actions should be recommended
  if updates are needed to the project management plan or organizational process assets.

## Slide 55: Tools and Techniques for Managing Project Teams
Observation and conversation
Project performance appraisals
Interpersonal skills
Conflict management

## Slide 56: Conflict Handling Modes
Confrontation: Directly face a conflict using a problem-solving approach
Compromise: Use a give-and-take approach
Smoothing: De-emphasize areas of difference and emphasize areas of agreement
Forcing: The win-lose approach
Withdrawal: Retreat or withdraw from an actual or potential disagreement
Collaborating: Decision makers incorporate different viewpoints and insights to develop consensus and commitment

## Slide 57: Figure 9-11. Conflict Handling Modes

## Slide 58: Conflict Can Be Good
Conflict often produces important results, such as new ideas, better alternatives, and motivation to work harder and more collaboratively
Groupthink: Conformance to the values or ethical standards of a group. Groupthink can develop if there are no conflicting viewpoints
Research suggests that task-related conflict often improves team performance, but emotional conflict often depresses team performance

## Slide 59: Five Dysfunctions of a Team
Patrick Lencioni, author of several books on teams, says that “Teamwork remains the one sustainable competitive advantage that has been large untapped”*
The five dysfunctions of teams are
    Absence of trust
    Fear of conflict
    Lack of commitment
    Avoidance of accountability
    Inattention to results
*Lencioni, Patrick, “Overcoming the Five Dysfunctions of a Team,” Jossey-Bass: San Francisco, CA (2005), p. 3.

## Slide 60: General Advice on Teams, Part 1
Be patient and kind with your team
Fix the problem instead of blaming people
Establish regular, effective meetings
Allow time for teams to go through the basic team-building stages
Limit the size of work teams to three to seven members

## Slide 61: General Advice on Teams, Part 2
Plan some social activities to help project team members and other stakeholders get to know each other better
Stress team identity
Nurture team members and encourage them to help each other
Take additional actions to work with virtual team members

## Slide 62: Using Software to Assist in Human Resource Management
Software can help in producing RAMS and resource histograms
Project management software includes several features related to human resource management such as
  Assigning resources
  Identifying potential resource shortages or underutilization
  Leveling resources

## Slide 63: Project Resource Management Involves Much More Than Using Software
Project managers must
  Treat people with consideration and respect
  Understand what motivates them
  Communicate carefully with them
Focus on your goal of enabling project team members to deliver their best work

## Slide 64: Chapter Summary
Project human resource management includes the processes required to make the most effective use of the people involved with a project
Main processes include
  Plan human resource management
  Acquire project team
  Develop project team
  Manage project team